# Week Jan 26-30

## Meetings

| Meeting | Date | Content |
| --- | --- | --- |
| VoCS mid-term | Jan 26 (Mon) | VoCS training network administration Presentation of all supervisors & PhD students |
| Optimization strategies for live spectrograms w/ Nicolas Reyman Forkani (former ENES intern) | Jan 29 (Thu) | Nicolas demonstrated three spectrographic tools he implemented for the Seeing Sound project, and explained the code Discussed performance optimization strategies: C++ vs Python vs JS, CPU vs GPU, signal processing on backend vs frontend (Awaiting Nicolas to share the full code) |

## Tasks, Progress, and Plans

| Task | Status | Progress | Next Steps |
| --- | --- | --- | --- |
| Sound library (Nonverbal vocalisations & Baby cries) | In progress | Prototyped audio + spectrogram generation pipeline Tested using Beyond Speech dataset Set up MEGA cloud drive (20GB free plan) | Collect baby cry audio from Emmalie Try NAS for cloud sync & consult UJM IT support (Angelique) |
| Live spectrogram | In progress | Migrated Quentin’s code from CPU to GPU (Decided not to adapt Chrome Music Lab's code directly, but keep it as reference) | Re-design the UI Add color pickers Animate fade-in/out effect |
| Eye tracker setup | Planned | - | Setup with Emmalie next week |